WEEK 1 TASK

Agribusiness Data
Analysis Planning

A structured plan for collecting, cleaning, analyzing, and interpreting public agricultural data

| Report Details | Information |
| --- | --- |
| Student | Amisha Urang |
| Program / Internship | YUVA Intern |
| Academic Background | Data Science Student — IIT Madras |
| Task | Week 1: Agribusiness Data Analysis Planning |
| Report Type | Research and Analysis Planning Document |
| Prepared | October 2026 |

Prepared for internship submission. This document presents a proposed analytical plan; it does not claim that the proposed datasets have already been collected or analyzed.

# 1. Executive Summary

This report presents a structured plan for analyzing publicly available agribusiness data, with a focus on agricultural production, crop yield, market prices, arrivals, weather conditions, resource utilization, and related factors. The objective is to establish a reproducible workflow that can later support exploratory data analysis, trend identification, and forecasting of agricultural market indicators.

The proposed approach combines Indian government data with internationally comparable agricultural statistics. The Open Government Data (OGD) Platform provides agriculture datasets, including district-, crop-, season-, and year-wise production information. Agmarknet provides agricultural market price and arrivals information, while the India Meteorological Department (IMD) provides rainfall and weather data. FAOSTAT provides internationally comparable food and agriculture datasets. These sources are selected because they cover complementary dimensions of the agribusiness ecosystem.

# 2. Objective

Develop a clear and reproducible strategy for collecting publicly available agribusiness data.

Identify key indicators relevant to agricultural production, market behavior, and resource utilization.

Define data cleaning and quality-control procedures before analysis.

Use descriptive statistics, trend analysis, correlation analysis, visualization, and time-series methods as appropriate.

Create a realistic timeline with milestones for collection, preparation, analysis, interpretation, and reporting.

Establish a foundation for future agricultural market trend and forecasting work.

# 3. Research Rationale

Agribusiness outcomes are influenced by multiple interacting factors. Crop output depends on cultivated area, yield, weather, irrigation, inputs, and production practices, while market prices can be affected by arrivals, seasonality, supply conditions, and other market forces. A data-driven approach can organize these variables into a common analytical framework.

The project therefore treats agriculture as a multi-dimensional data problem rather than relying on a single indicator. For example, crop production should be examined together with area harvested and yield, while price movements can be compared with market arrivals and weather indicators. This approach improves the interpretability of observed trends and provides a stronger basis for subsequent forecasting.

# 4. Proposed Public Data Sources

The following sources are proposed for the project. Dataset availability, update frequency, definitions, and licensing should be checked again immediately before collection.

| Source | Proposed Data | Use in Analysis |
| --- | --- | --- |
| Open Government Data (data.gov.in) | Crop production, cultivated/harvested area, production by district/crop/season/year | Production trends, yield calculations, geographic comparisons |
| Agmarknet | Mandi/market prices, arrivals, commodity and variety information | Price trends, volatility, seasonal behavior, price–arrival relationships |
| India Meteorological Department (IMD) | District/state rainfall, weather observations and forecasts | Weather variability, rainfall departures, weather–production relationships |
| FAOSTAT | Crop/livestock production, land use, fertilizers, producer prices, trade and related indicators | Cross-checking, benchmarking, and broader agricultural context |
| FAO Food & Agriculture Microdata Catalogue (FAM) | Publicly available agriculture/household/farm survey metadata and microdata inventory | Potential survey-level variables where appropriate and permitted |

## 4.1 Source Selection Criteria

Authority: Prefer official government or intergovernmental statistical sources.

Relevance: Variables must directly support the research questions and selected agricultural commodities.

Granularity: Prefer datasets with consistent geographic, temporal, and commodity identifiers.

Coverage: Prefer sufficiently long time series for trend and forecasting analysis.

Documentation: Dataset definitions, units, metadata, and methodology should be available.

Reproducibility: The source should permit a documented and repeatable data-access process.

# 5. Key Indicators and Metrics

| Category | Indicator | Definition / Analytical Purpose |
| --- | --- | --- |
| Production | Production volume | Total quantity produced; used for production trends and comparisons. |
| Production | Area harvested | Cultivated/harvested area associated with a crop and period. |
| Production | Crop yield | Production divided by relevant harvested area, subject to consistent units. |
| Market | Modal/representative price | Market price measure used to study price levels and trends. |
| Market | Minimum / maximum price | Range of observed market prices; useful for dispersion and market variation. |
| Market | Market arrivals | Quantity arriving at a market; used to examine supply-side movements. |
| Market | Price volatility | Variation in prices over time, measured using suitable dispersion or return-based metrics. |
| Weather | Rainfall | Daily/weekly/monthly rainfall used to characterize water availability and variability. |
| Weather | Rainfall departure | Difference between observed and normal rainfall, expressed according to source definition. |
| Resources | Fertilizer/input use | Input intensity or quantity where consistent data are available. |
| Trade | Import/export quantity and value | Used to understand external-market exposure and commodity flows. |

# 6. Proposed Research Questions

How have production volumes and harvested areas changed over time for selected crops?

How does crop yield vary across years, seasons, and geographic regions?

What seasonal patterns are visible in agricultural market prices and arrivals?

How volatile are prices for selected commodities, and does volatility vary by market or season?

Is there an observable relationship between market arrivals and prices?

How do rainfall levels and rainfall departures correspond with production or yield changes?

Which indicators show persistent upward, downward, or seasonal patterns?

Which variables appear suitable for a future forecasting model, subject to data quality and sufficient historical coverage?

# 7. Step-by-Step Data Collection and Analysis Plan

| Step | Planned Activity |
| --- | --- |
| Step 1 — Define scope | Select 2–3 agricultural commodities, geographic level, study period, and target outcomes. Record all definitions and units before downloading data. |
| Step 2 — Source discovery | Locate official datasets and record source name, dataset title, URL, publisher, update date, frequency, unit, and access method. |
| Step 3 — Data acquisition | Download available CSV/Excel/API data. Preserve the original files as read-only raw data. |
| Step 4 — Data dictionary | Create a variable dictionary covering column name, meaning, data type, unit, source, expected range, and transformation rules. |
| Step 5 — Data cleaning | Standardize column names, dates, crop names, locations, units, and numeric formats. Remove duplicates and investigate missing or inconsistent records. |
| Step 6 — Data validation | Check row counts, duplicate keys, impossible values, missingness, date continuity, unit consistency, and selected records against source documentation. |
| Step 7 — Data integration | Join production, market, and weather datasets using common identifiers such as crop, location, date/year, and season. Keep unmatched records documented. |
| Step 8 — Exploratory Data Analysis | Calculate descriptive statistics and create time-series, distribution, comparison, and relationship visualizations. |
| Step 9 — Trend analysis | Measure year-over-year changes, moving averages, seasonal patterns, growth rates, and volatility where appropriate. |
| Step 10 — Relationship analysis | Use correlation and other suitable statistical methods to explore associations between production, prices, arrivals, and weather. Treat correlation as association, not proof of causation. |
| Step 11 — Forecasting preparation | Assess time-series continuity, seasonality, outliers, and train/test structure before selecting a forecasting method. |
| Step 12 — Interpretation and reporting | Translate results into concise findings, limitations, assumptions, and recommendations for further analysis. Document all transformations for reproducibility. |

# 8. Data Cleaning and Quality-Control Framework

| Issue | Detection | Treatment / Documentation |
| --- | --- | --- |
| Missing values | Null counts by variable and time period | Assess source meaning; retain, impute, or exclude only with justification. |
| Duplicate records | Duplicate key checks | Remove true duplicates; investigate conflicting duplicates before removal. |
| Inconsistent names | Unique-value inspection | Create standardized mapping for crop, market, district, and state names. |
| Unit mismatch | Compare metadata and magnitude | Convert to a common unit and retain original unit information. |
| Date inconsistencies | Date parsing and frequency checks | Standardize dates and document aggregation rules. |
| Outliers | IQR/z-score/time-series inspection | Investigate source and context before deciding whether to retain or transform. |
| Impossible values | Domain/range checks | Flag values such as negative production or invalid dates for investigation. |
| Join mismatches | Unmatched-key report | Maintain a reconciliation log rather than silently dropping observations. |

# 9. Analytical Methods

| Method | Application | Expected Output |
| --- | --- | --- |
| Descriptive statistics | Mean, median, minimum, maximum, standard deviation, quantiles | Baseline understanding of distributions and variation |
| Trend analysis | Year-over-year change, growth rate, moving average | Long-term and short-term direction of indicators |
| Seasonality analysis | Monthly/seasonal comparisons | Recurring seasonal patterns |
| Correlation analysis | Price vs arrivals; yield vs rainfall, etc. | Association matrix / selected relationship plots |
| Visualization | Line, bar, scatter, box and heatmap charts | Clear communication of patterns and anomalies |
| Time-series analysis | Decomposition and suitable forecasting models after diagnostics | Forecasts with uncertainty measures where supported |

# 10. Forecasting Approach (Future Phase)

Forecasting will be considered only after data quality, time-series continuity, seasonality, and sample size are assessed. Candidate approaches may include baseline methods, moving averages, exponential smoothing, ARIMA-family models, or other methods justified by the data. Model selection will be based on out-of-sample validation rather than choosing a method solely because it is more complex.

Define the target variable and forecasting horizon.

Sort observations chronologically and prevent future information from entering training data.

Create a time-based train/validation/test split where data volume permits.

Establish a simple baseline forecast for comparison.

Evaluate candidate models using appropriate error metrics such as MAE, RMSE, or MAPE where mathematically appropriate.

Document assumptions, limitations, and uncertainty.

# 11. Project Timeline and Milestones

| Week | Milestone | Key Deliverables |
| --- | --- | --- |
| Week 1 | Planning & source identification | Research rationale, data-source inventory, metrics, workflow, timeline |
| Week 2 | Data collection | Raw datasets, source log, metadata/data dictionary |
| Week 3 | Cleaning & validation | Clean datasets, quality-control log, reproducible cleaning steps |
| Week 4 | Exploratory analysis | Descriptive statistics and initial visualizations |
| Week 5 | Trend & relationship analysis | Trend tables, seasonal analysis, correlation/association analysis |
| Week 6 | Forecasting preparation | Time-series diagnostics, baseline, model candidates |
| Week 7 | Forecasting & validation | Validated model results and error metrics |
| Week 8 | Final reporting | Interpretation, limitations, charts, final report and reproducibility notes |

# 12. Tools and Technical Workflow

Python: pandas and NumPy for data handling and numerical analysis.

Matplotlib / other appropriate visualization libraries for charts.

Jupyter Notebook or a comparable notebook environment for documented analysis.

Git and GitHub for version control and reproducibility, where required by the internship.

Excel/CSV for initial inspection and lightweight validation.

APIs or programmatic downloads where an official source provides a documented access method.

# 13. Risks, Limitations, and Mitigation

| Potential Risk | Impact | Mitigation |
| --- | --- | --- |
| Different definitions across sources | Incorrect comparisons | Read metadata and harmonize definitions before integration. |
| Missing or delayed observations | Incomplete time series | Record missingness and avoid unsupported assumptions. |
| Changes in market/data collection practices | Breaks in comparability | Inspect metadata and flag structural breaks. |
| Different geographic boundaries | Invalid regional comparisons | Use stable identifiers or document boundary changes. |
| Price/arrival reporting differences | Biased market comparisons | Compare like-for-like markets and commodities. |
| Forecast uncertainty | Overconfident conclusions | Use validation, baselines, uncertainty intervals where available, and clear limitations. |

# 14. Expected Outcomes

A documented inventory of reliable public agribusiness data sources.

A clean and well-documented analytical dataset for selected crops/markets.

A set of descriptive statistics and visualizations explaining production, price, arrivals, and weather patterns.

Identification of important trends, seasonal patterns, and observable associations.

A reproducible workflow that can be extended into forecasting and deeper analysis.

A professional final report that clearly separates observed facts, analytical results, assumptions, and limitations.

# 15. Conclusion

This Week 1 plan establishes the foundation for a data-driven agribusiness analysis project. The proposed workflow prioritizes authoritative public sources, transparent data preparation, reproducible analysis, and appropriate validation. The next stage should focus on selecting a manageable set of commodities and locations, collecting the raw datasets, and building the data dictionary and quality-control framework before any forecasting conclusions are attempted.

# 16. References / Official Data Sources

Open Government Data (OGD) Platform India — Agriculture — Government of India agriculture data catalogue.
https://data.gov.in/sector/agriculture

OGD Platform India — District-wise, season-wise crop production statistics — Crop area and production by district, crop, season and year.
https://www.data.gov.in/catalog/district-wise-season-wise-crop-production-statistics-0

Agmarknet — Agricultural Marketing Information — Agricultural market prices, arrivals and market information.
https://agmarknet.gov.in/

India Meteorological Department — Rainfall Information — State/district and time-based rainfall information.
https://mausam.imd.gov.in/responsive/rainfallinformation_state.php

India Meteorological Department — API Reference — Documented weather and rainfall API endpoints.
https://api.imd.gov.in/public/api_reference.html

FAOSTAT — Food and Agriculture Data — International food and agriculture statistics.
https://faostat.fao.org/

FAO Statistics — Agriculture Data Collection — Methodology and data-collection information for agricultural statistics.
https://www.fao.org/statistics/data-collection/agriculture/

FAO Food & Agriculture Microdata Catalogue — Catalogue of publicly available agriculture and related survey microdata.
https://www.fao.org/food-agriculture-microdata/en

Source note: URLs and source descriptions were checked against official source pages during preparation of this report in October 2026. Dataset contents and availability can change; the collection stage should re-check the latest metadata and release dates.